## Shipments
Shipment ID | Final Location | Open Status | Mode | Gross Weight Tons | Port Date | MOSB Date | Site Date | eBL Match | BOE Complete | FANR Ready | ECAS Ready | CICPA Ready | FRA Ready | DOT Ready | Weather Alert | MOSB Utilization Pct | Warehouse 1 Date
AGI-001 | AGI | At WH pending site | C | 45 | 2026-03-01 |  |  | TRUE | TRUE |  |  | TRUE | FALSE |  | FALSE | 70
DAS-001 | DAS | In transit | B | 20 | 2026-03-01 |  |  | TRUE | TRUE |  | TRUE | TRUE | TRUE |  | FALSE | 72
MIR-001 | MIR | At WH pending site | A | 120 | 2026-03-02 |  |  | TRUE | TRUE |  |  | TRUE |  | FALSE | FALSE | 88 | 2026-03-04
SHU-001 | SHU | Delivered to site | B | 85 | 2026-03-01 |  | 2026-03-05 | TRUE | TRUE |  |  | TRUE |  |  | FALSE | 60
AGI-002 | AGI | At WH pending site | C | 25 | 2026-03-01 | 2026-03-06 |  | TRUE | FALSE | FALSE | TRUE | TRUE | FALSE |  | TRUE | 105

## Alternate
Shipment ID | Final Location | Open Status | Mode | Gross Weight Tons | Port Date | MOSB Date | Site Date | eBL Match | BOE Complete | FANR Ready | ECAS Ready | CICPA Ready | FRA Ready | DOT Ready | Weather Alert | MOSB Utilization Pct | Warehouse 1 Date
AGI-001 | AGI | At WH pending site | C | 45 | 2026-03-01 |  |  | TRUE | TRUE |  |  | TRUE | FALSE |  | FALSE | 70
DAS-001 | DAS | In transit | B | 20 | 2026-03-01 |  |  | TRUE | TRUE |  | TRUE | TRUE | TRUE |  | FALSE | 72
MIR-001 | MIR | At WH pending site | A | 120 | 2026-03-02 |  |  | TRUE | TRUE |  |  | TRUE |  | FALSE | FALSE | 88 | 2026-03-04
SHU-001 | SHU | Delivered to site | B | 85 | 2026-03-01 |  | 2026-03-05 | TRUE | TRUE |  |  | TRUE |  |  | FALSE | 60
AGI-002 | AGI | At WH pending site | C | 25 | 2026-03-01 | 2026-03-06 |  | TRUE | FALSE | FALSE | TRUE | TRUE | FALSE |  | TRUE | 105